## Instructions
DataDab editable companion workbook | saas-migration-guide-hard-questions
Version | v1
Built at UTC | 2026-10-12T18:19:17.365367+00:00
Purpose | Planning / manual recording aid. No measured results, account connection, certification, or revenue forecast.
Use | Read the companion article; assign owners; complete fields with verified evidence.
Unknown vs zero | Leave unknown inputs blank. Enter numeric 0 only for a known zero. Never convert missing facts to zero.
Privacy | Keep buyer identifiers, customer information, and private source references only in approved internal storage.
Examples | Question prompts are prompts. Any Example sheet is explicitly fictional and excluded from reporting.
Formulas | Formula results require recalculation in your spreadsheet application. Check the formulas and assumptions before using totals.
Costs | USD estimates only; retain units, scope, and term. Known cost totals can be partial when rows remain uncosted.
Rows | 120 prepared input rows. Extend formulas and validation ranges if adding rows.
Verification | Source verification and asset creation dates do not set historical publication dates.
Effort formula | Known estimate = hours × hourly rate + other cost. All inputs must be numeric; enter 0 for a known absence of other cost.

## Scope
Source product / version | Destination product / version | Supported route | Plan / permission requirements | Included | Excluded | Official source | Verified date | Owner

## Inventory
Item | Source location | Destination treatment | Owner | Sensitivity / retention | Required identifiers / relationships | Verification method | Result / evidence
Core records
Relationships
Attachments / history
Rules / automations
Permissions
Reports
Integrations

## Responsibilities
Task | Vendor owner | Buyer owner | Partner owner | Dependency | Ready condition | Due date | Status

## Rehearsal
Check | Environment / permitted data | Sample definition | Acceptance criterion | Owner | Result | Evidence | Defect / next action
Required fields and identifiers |  |  |  |  | Not tested
Relationships |  |  |  |  | Not tested
Agreed count / total checks |  |  |  |  | Not tested
Permissions |  |  |  |  | Not tested
Critical user task |  |  |  |  | Not tested
Downstream integration |  |  |  |  | Not tested
Recovery procedure |  |  |  |  | Not tested

## Cutover
Task | Owner | Prerequisites | Decision point / deadline | Acceptance check | Recovery route and limits | Go / no-go owner | Evidence / result

## Effort
Task | Scope | Estimated hours | Rate USD per hour | Other cost USD | Known estimate USD | Assumptions | Owner